## Road Map
Accounting Software (Xero)
|  |  | Cycle 1 | Cycle 2 | Cycle 3
Application Modules | Feature Backlog | Story Points | Test Completion Date- 04/19/2024 | Test Completion Date- 05/03/2024 | Test Completion Date- 05/10/2024
4. Financial Data Entry | 4.1 Group transactions by pay period | 3
| 4.2 Export transactions report | 5
| 4.3 Draft payment | 2
| 4.4 Publish payment | 3
| 4.5 Add account to chart of accounts | 2
| 4.6 Add bank account to chart of accounts | 3
| 4.7 Import banking data from CSV | 8
| 4.8 Export chart of accounts as CSV | 3
| 4.9 Print chart of accoutns report | 3
| 4.10 Archive account from chart of accounts | 2
| 4.11 Create new journal | 3
| 4.12 Create new repeating journal entry | 5
| 4.13 Copy a journal entry | 3
| 4.14 Edit a journal entry | 3
| 4.15 Reverse a journal entry | 3
| 4.16 Set an existing journal entry to repeat | 3
| 4.17 Void a journal entry | 3
| 4.18 Archive a journal | 3
| 4.19 Show journal entry history | 2
| 4.20 Add a node to journal | 3
| 4.21 Search a journal | 2
5. Bank Feeds and Reconciliations | 5.1 Automate Data Import | 5
| 5.2 Display Real-time Updates | 3
| 5.3 Perform Bank Reconciliation | 8
| 5.4 Categorizing and Coding | 5
| 5.5 Managing Bank Account | 3
| 5.6 Ensuring Security | 5
| 5.7 Matching Transactions | 5
| 5.8 Creating Rule Template | 3
| 5.9 Managing Rules | 3
| 5.10 Applying Custom Criteria | 3
| 5.11 Prioritizing Orders | 2
| 5.12 Assigning Account Codes | 3
| 5.13 Handling Tax Treatment | 5
| 5.14 Managing Sub-Accounts | 3
| 5.15 Classifying Accounts | 3
| 5.16 Editing GL Accounts | 3
| 5.17 Conducting GL Account Operations | 5
| 5.18 Performing Bulk Reconciliation | 8
| 5.19 Generating Reconciliation Reports | 5
| 5.20 Accessing Transaction History | 3
| 5.21 Tracking Audit Trail | 3
| 5.22 Conducting Reporting and Analysis | 5
| 5.23 Reconciling Bank Statement | 8